## Sheet1
Issue ID | Issue Description | Expected behavior | Actual behavior | Root cause | Status | Priority | Quick action | Long-term action | Reporter | Assignee | Date Created | Due Date | Date Closed | Comments
OMS-IMP-PMP-01 | The file are not located in the right place on GitHub | PMP should contain IMP, review&approval process, Change management plan, and CMP | PMP is in the same place with IMP, review&approval process, Change management plan, and CMP | Misanderstanding of the project roles | in progress | High | Report the change in the Change management plan | Modify the branching of the files in a correct way | Salma | Ghada | 30/3/2024 | 31/3/2024

## Sheet2
High
Medium
Low | in review/open
in progress
on hold
resolved/done