## Sheet1
2024-02-05 | Document Name | Version Number | Author | Reviewer | Due Date | Comments
OMS-REV-LLD-01 | OnlineMobileStore_Design_LLD | 2 | Salma Mohamed,sama wagy,salma khaled | eng/Amr Helal | 29/4/2024 | add function name to each of sequence diagrams and remove flowchart of logout supplier.
OMS-REV-LOGFR-02 | OnlineMobileStore_Code/login front end | 1 | Mario Ramzy | Salma Mohamed | 2024-02-05 | The front end has no bad comments.
OMS-REV-REGFR-03 | OnlineMobileStore_Code/ registeration front end | 1 | Mario Ramzy | Salma Khaled | 2024-02-05 | The front end has no bad comments.
OMS-REV-LOGBK-04 | OnlineMobileStore_Code/login Back end | 1 | Sama Wagdy | Salma Mohamed | 2024-03-05 | The front end has no bad comments.
OMS-REV-REDBK-05 | OnlineMobileStore_Code/ registeration Back end | 1 | Sama Wagdy | ghada hassan | 2024-05-05 | The front end has no bad comments.
OMS-REV-ADMFR-06 | OnlineMobileStore_Code/Admin front end | 1 | ghada hassan | Salma Mohamed | 2024-05-05 | The front end has no poor / bad comments.
OMS-REV-ADMBK-07 | OnlineMobileStore_Code/ Admin back end | 1 | Sama Wagdy | Salma Khaled | 2024-06-05 | There is no confirmation steps that may make some data loss without ability to get it back.
OMS-REV-SUPFR-08 | OnlineMobileStore_Code/Supplier front end | 1 | Salma Khaled | Mario Ramzy | 2024-06-05 | The front end has no poor / bad comments.
OMS-REV-SUPBK-09 | OnlineMobileStore_Code/Supplier back end | 1 | Sama Wagdy | Salma Mohamed | 2024-06-05 | The supplier back end has no poor / bad comments.
OMS-REV-DB-10 | OnlineMobileStore_Code/Data Base Implementation | 1 | Mohamed el-kassas | Sama Wagdy | 2024-06-05 | there is no comments for data base implementation.
OMS-REV-CRDFR-11 | OnlineMobileStore_Code/Client module/card front end | 1 | Salma Khaled | Sama Wagdy | 2024-06-05 | The front end has no poor / bad comments.
OMS-REV-CRDBK-12 | OnlineMobileStore_Code/Client module/card back end | 1 | Sama Wagdy | Salma Khaled | 2024-07-05 | The card back end has no bad comments.
OMS-REV-CLFR-13 | OnlineMobileStore_Code /Client module/client dashoard front end | 1 | Salma Khaled | Mohamed el-kassas | 2024-07-05 | The front end has no bad comments.
OMS-REV-CLBK-14 | OnlineMobileStore_Code /Client module/client dashoard Back end | 1 | Sama Wagdy | Salma Mohamed | 2024-08-05 | The client dashboard back end has no bad comments.
OMS-REV-HIFR-15 | OnlineMobileStore_Code /Client module/Purchase history front end | 1 | Salma Khaled | Mohamed el-kassas | 2024-08-05 | The front end has no poor / bad comments.
OMS-REV-HIBK-16 | OnlineMobileStore_Code /Client module/Purchase history Back end | 1 | Sama Wagdy | Mario Ramzy | 2024-09-05 | The client puchase history back end has no bad comments.
OMS-REV-RTM-17 | OnlineMobileStore_RTM | 1 | Salma Mohamed | Mohamed el-kassas | 2024-10-05 | No comments
OMS-REV-LOGFR-18 | OnlineMobileStore_Code/login front end | 1 | Mario Ramzy | eng/Amr Helal | 2024-03-05 | The login interface is confusing, with poor labeling and unclear instructions, leading to a bad UX.
OMS-REV-REGFR-19 | OnlineMobileStore_Code/ registeration front end | 1 | Mario Ramzy | eng/Amr Helal | 2024-03-05 | same comment as login and registeration have the same UI.
OMS-REV-LOGBK-20 | OnlineMobileStore_Code/login Back end | 1 | Sama Wagdy | eng/Amr Helal | 2024-04-05 | The backend token management system fails to implement proper validation, expiration controlshe
OMS-REV-REDBK-21 | OnlineMobileStore_Code/ registeration Back end | 1 | Sama Wagdy | eng/Amr Helal | 2024-05-05 | It allows for the submission of incomplete or invalid data, which could lead to data corruption or security vulnerabilities.

## Sheet2
2024-02-05 | Document Name | Version Number | Author | Reviewer | Due Date | Comments
OMS-REV-LLD-01 | OnlineMobileStore_Design_LLD | 2 | Salma Mohamed,sama wagy,salma khaled | eng/Amr Helal | 29/4/2024 | add function name to each of sequence diagrams and remove flowchart of logout supplier.
OMS-REV-LOG-02 | OnlineMobileStore_Code/login module | 1 | Sama Wagdy | Salma Mohamed | 2024-08-05 | no comments.
OMS-REV-REG-03 | OnlineMobileStore_Code/ registeration fmodule | 1 | Sama Wagdy | sama wagdy | 2024-08-05 | It has a problem with navigating to next page.
OMS-REV-ADM-04 | OnlineMobileStore_Code/admin module | 1 | Salma Mohamed | mario | 2024-08-05 | there is a conflict between delete useer and delete item
OMS-REV-SUPP-05 | OnlineMobileStore_Code/ supplier module | 1 | Sama Wagdy | kassas | 2024-09-05 | logout function is not implented
OMS-REV-CLNT-06 | OnlineMobileStore_Code/client module | 1 | salma khaled | ? | ? | ?
OMS-REV-RTM-7 | OnlineMobileStore_RTM | 1 | Salma Mohamed | salma khaled | 2024-10-05 | in code we use code file name , not function name
OMS-REV-LG-8 | OnlineMobileStore_Code/login module | 1 | sama wagdy | eng/Amr Helal | 2024-09-05 | password not hashed = security bug.
OMS-REV-RG-9 | OnlineMobileStore_Code/ registeration fmodule | 1 | sama wagdy | eng/Amr Helal | 2024-09-05 | password not hashed = security bug.
OMS-REV-ADM-10 | OnlineMobileStore_Code/admin module | 1 | Salma Mohamed | eng/Amr Helal | 2024-10-05 | function name not as in the design.
OMS-REV-SUP-11 | OnlineMobileStore_Code/ supplier module | 1 | Sama Wagdy | eng/Amr Helal | 2024-10-05 | no comments.